10. Project Management and Risks

10.1 Repository and tools

- Git repository: GitHub, private, access for supervisor and committee; branch protection on main; changes via pull requests reviewed by another team member; each submission tagged as required by the department (first submission: prob-period-1); tags are never moved.

- YouTrack project: key MED; tasks have an owner, acceptance criteria, deadline and priority. Task identifiers appear in branch/commit names (e.g. MED-13-context-diagram); historical MSA task IDs in the initial plan remain for traceability.

- CI: GitHub Actions - lint, tests, diagram rendering check.

Repository structure

medguard/

├── README.md          project, team, scope, status, links

├── docs/              proposal, reviews, requirements

│   └── adr/           architecture decision records

├── diagrams/          editable .drawio/.puml sources + PNG/SVG exports

├── prototype/         MedGuard UI prototype PDF and design assets

├── backend/           FastAPI application

├── ai/                NLP parser, RAG, explainer, eval

├── frontend/          Next.js application

├── data/              offline synthetic-data generation, rule-base and label-preparation scripts

├── tests/             unit, integration, e2e

├── docker-compose.yml

├── .env.example       placeholder values only

└── .gitignore

10.2 Roles and responsibilities

Each member leads assigned workstreams and supports others. Changes are submitted through pull requests and reviewed by another team member before merging. The responsibilities below describe the agreed project plan, not a claim that every feature has already been implemented.

| Member | Roles | Primary responsibility | Reviews |
| --- | --- | --- | --- |
| Yertay Altynay | ML Engineer (lead), Research Head, Backend Developer, Frontend Developer | NLP anamnesis parser, local RAG retrieval, explanation generator and evidence support check; rule-base research, literature review, evaluation scripts and experiments (Section 9); assigned backend and web UI contributions. | ML and research pull requests |
| Salemkan Aknur | Head of Backend, DevOps, Business Analyst, UI/UX Designer, ML Developer | Backend architecture, database schema, FastAPI REST API, team-script synthetic database generator, RxNorm normalisation, Drug Safety Engine, schedule generator, authentication/RBAC, audit, Docker and CI; requirements, physician interview and AI integration. | Backend and DevOps pull requests |
| Nuraly Nuray | Project Manager, Head of Frontend, QA Engineer, ML Developer | Project planning, YouTrack and supervisor communication; doctor dashboard, patient web interface, read-only administrator dashboard (usage counts, clinics, doctors and pseudonymous logs), Telegram bot interface and reminders; end-to-end, QA and usability tests; test-scenario labelling; Sections 1, 4, 5 and 10. | Frontend pull requests and documentation |

10.3 Task plan until 24 October 2026

| Task | Owner | Due | Acceptance criterion |
| --- | --- | --- | --- |
| MSA-1 Create GitHub repo, structure, .gitignore, README; invite team and supervisor | Aknur and Nuray | 22 Oct | Supervisor has access; README has all required sections |
| MSA-2 Set up YouTrack project and board; create tasks with owners, priorities, deadlines | Aknur and Altynay | 19 Oct | Link in README; all tasks assigned |
| MSA-3 Project proposal and scope (Section 1), updated to MedGuard requirements | Nuray | 20 Oct | Reviewed by supervisor |
| MSA-4 Physician interview P1 and evidence of relevance (Section 2) | Aknur | 23 Oct | Anonymised P1 interview and evidence table; signed consent held outside repository |
| MSA-5 Literature review and analysis table | Altynay | 21 Oct | ≥ 12 sources, ≥ 8 scientific, table complete |
| MSA-6 Existing system comparison | Nuray | 21 Oct | 5 systems × 10 criteria with source links |
| MSA-7 Technology comparison and architecture decisions | Nuray | 21 Oct | 6 decisions documented as ADRs |
| MSA-8 Requirements specification and acceptance criteria (MED-8) | Aknur | 22 Oct | FR-01–FR-46 and NFR-01–NFR-22; role and privacy constraints reviewed |
| MSA-9 Context, component and use-case diagrams (MED-13, MED-17) | Altynay | 22 Oct | Editable sources plus PNG/SVG exports; three human roles and current components |
| MSA-10 Three-role UI prototype (MED-18) | Aknur | 23 Oct | 22-page PDF; doctor, patient and administrator flows; requirement mapping in Table 7 |
| MSA-11 Verification and evaluation plan | Altynay | 22 Oct | Section 9 approved; testing part reviewed by QA |
| MSA-12 Pilot: generate synthetic patients with team scripts; normalise 10 drug names via RxNorm API | Aknur | 23 Oct | Reproducible synthetic-data generator with fixed seed; short normalisation report |
| MSA-13 Rule-base pilot: DDInter records for in-scope drug groups | Altynay | 23 Oct | 20+ records with severity and source; Rule format agreed with backend |
| MSA-14 Supervisor review, feedback log, tag prob-period-1, submission form | Nuray | 24 Oct, 18:00 | Tag created; feedback table (Section 11) filled; form submitted |

10.4 Risks

Table 10.1. Risk register

| ID | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Medical complexity exceeds team expertise; incorrect rules | High | High | Narrow scope to 4 drug groups; rules come only from DDInter and labels, never invented; expert review of a sample; position as decision support |
| R2 | No access to clinicians for interviews or expert review | Medium | High | Physician interview P1 completed; seek additional expert review where feasible; distinguish verified evidence from assumptions and document limitations. |
| R3 | LLM hallucinations in explanations | High | Medium | LLM cannot create alerts; support check; fallback to rule text; measured hallucination rate |
| R4 | External APIs unavailable or rate-limited (RxNav, openFDA) | Medium | Medium | Cache external drug-reference responses and prepare versioned local label snapshots before runtime; no patient data sent to external APIs. |
| R5 | Insufficient hardware for local LLM | Medium | Medium | Use quantised local models or smaller extraction models; benchmark hardware and latency. Hosted APIs, if compared experimentally, receive synthetic data only. |
| R6 | Synthetic notes too simple; NLP results overestimated | Medium | Medium | LLM paraphrasing, abbreviations and typos added; manual realistic notes subset; report limitation |
| R7 | Licensing of knowledge sources | Low | High | Use DDInter (CC BY-NC-SA, non-commercial), public-domain FDA labels, NLM terms; attribute sources in UI and thesis |
| R8 | Uneven workload or member unavailable | Medium | Medium | Weekly team sync, YouTrack board, secondary owners and cross-review of pull requests. |
| R9 | Scope creep (additional drug groups, mobile/PWA interfaces, production EHR integration) | Medium | Medium | Changes require supervisor approval; keep the diploma deliverable desktop web-only, use Telegram for reminders, and exclude production EHR integration. |

10.5 Dependencies

- Team-generated synthetic patient database and reproducible generation scripts (fixed random seed); no Synthea import in the product.

- RxNorm/RxNav (NLM) for drug-name normalisation and reference data; cache approved responses; no patient information is sent.

- openFDA Drug Label and DailyMed as sources for offline label ingestion and local, versioned snapshots.

- DDInter 2.0 (CC BY-NC-SA 4.0) for offline rule-base preparation, subject to attribution and licence terms.

- Local LLM runtime (e.g. Ollama/vLLM) and adequate CPU/GPU/RAM; patient text remains within the clinic deployment.

- Anonymised physician interview P1 and any additional clinicians or pharmacists available for expert validation; consent records kept outside the repository.

- Supervisor availability for weekly reviews.